## Sheet1 (hidden)
Draft Road Map for the Disposal of the Harvested Mukula Logs and othe related Activities
No | Activity Description | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July
| Weeks | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Prepare Cabinet Memoranda on the disposal of Mukula logs
2 | SPV - Development of ToRs
3 | Resource Mobilisation
4 | SPV - Appointment/Confirmation
4 | Set Up of Satellite/Collection Centres
5 | Invitation - Individuals & Companies to declare quantities and location of Mukula Logs, (transfer to Satellite / Collection Centres)
6 | SPV - Logs to Satellite/Collection Centres
7 | Development of ToRs for the Valuation Team
8 | Constitution of Valuation Team
10 | Log Valuation Exercise (price setting)
11 | Engagement with Stakeholders & Traditional Leardership
12 | Disposal of Logs (auctioning at Satellite / Collection Centres
13 | SPV - Mopping uncollected/undeclared Mukula logs
14 | Review SI No. 94: The Forests (Export of Timber) Regulations 2015
15 | Consideration of lifting the ban on harvesting, trading and export of Mukula timber species
16 | Review of exisiting Concessions
17 | Undertake inventory of standing trees in selected concession areas
18 | Consider issuance of timber Concession licenses for 2022
19 | Monitoring and Evaluation Activities

## FORESTRY
Proposed Road Map for the Review and Amendment of Forests Act No.4 of 2015
No | Activity Description | Dec, 2024 |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct
| Weeks | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Draft and submit Cab Memo seeking Cabinet Approval in principal to amend Forests Act No. 4 of 2015
2 | Cabinet Approval of the Cab Memo
3 | Formation of the Core Team
4 | Desk Review of the Act (identify areas of amendment)
5 | Consolidation of proposed Amendments
6 | Drafting Instructions to AG’s Chambers
7 | Drafting of the Proposed Bill
8 | Regulatory Impact Assessment (BRRA)
9 | Provincial Consultation
10 | National Stakeholder Consultation
11 | Consolidation of Comments/submissions
12 | Final Stakeholders Validation
13 | Finalisation of the Bill
14 | Submission finalised Bill to Internal Legislation Committee (MoJ)
15 | Approval by the Internal Legislation Committee (MoJ)
16 | Preparation and submission of Cab Memo for Cabinet consideration