## ANNEX 9 - Min.Or.Req.for.Activ
|  | remark | trainees (recommended to follow) | trainers | CZ experts (number of CZ experts) (recommended to follow) | GE missions experts (pcs) - participants of study trip (compulsory to follow) | days spent in CZ - for preparatory work - and study trip conducting (man*days) (recommended to follow. With expeception of 3.1.2, 3.1.3, 3.2.1, 4.3.1, 4.3.2, 4.3.3, 5.3. Information about above-indicated sub-activities (3.1.2, 3.1.3, 3.2.1, 4.3.1, 4.3.2, 4.3.3, 5.3.) are compulsory to follow. | days in GE - missions man*days (compulsory to follow) | Workshop GE participants( No) (compulsory to follow) | Language (compulsory to follow)
Certain Minimal Organizational Requirements specified in this document has to be followed by the implementer. Column D and F are recommended to follow, whereas columns G, I, J, K are compulsoy to follow. Column H is partly compulsory to follow (see further explanation in column H). Compulsory or partly compulsory columns has to be followed during budget elaboration - based on the need and decission of implementer, these minimal requirments can be exceeded.
1. | ACTIVITY 1 - Area of EU directive 128/2009
Overall Output - Initial workshop on requirements of directive 128/2009 organized, Complex proposals for a) certification system of professional users of pesticides, b) establishment of system for control/inspection of pesticide spraying equipment elaborated and submitted to relevant authorities
1.1. | 1.1. Sustainable use of pesticides
1.1.1. | Initial workshop on requirements of directive 128/2009 | START OF THE PROJECT - JOINED 2 day WORKSHOP FOR 1.1.1, 1.2.1 AND 1.3.4 | NFA, MEPA, SLA, Multitest, Cooperating agencies, experts, (RDA, ICC, EIEC) | CZ expert (s) | 3 CZ experts needed for this sub-activity |  | 9 (Each from 3 experts will need 3 working days for preparation of this sub-activity) | 6 (Each from 3 experts will need 2 mission days in Georgia) | 70 participants | Simultaneous Translation _ English-Georgian
1.2. | 1.2. Certification of professional users of pesticides
1.2.1. | Continuation of initial Workshop - certification of profesional PPP users | START OF THE PROJECT - JOINED 2 day WORKSHOP FOR 1.1.1, 1.2.1 AND 1.3.4 | NFA (MEPA, RDA, ICC, EIEC) | CZ expert (s)
1.2.2. | Evaluation mission - Evaluation of the whole segment of professional users of pesticides in GE (distributors, advisors, services, farmers, other users) | 5 workning-day mission in GE | NFA | CZ expert (s) | 1 CZ expert needed for this sub-activity |  | 6 (1 Expert will need 6 working days for preparation of this sub-activity) | 5 (Expert will need 5 mission days in Georgia) |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
1.2.3. | Reccomendation of definition (s) of professional user of pesticides in Georgia (specification of each category) | 4 working day mission to GE, on-line cooperation | NFA (RDA, ICC, EIEC) | CZ expert (s) | 1 |  | 8 | 4 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
1.2.4. | Assistance in development of training and qualifying/ certification system for different categories of professional users of pesticides (distributors, advisers/consultants/services, farmers) | 5 working day mission to GE, on-line cooperation | NFA (RDA, ICC, EIEC) | CZ expert (s) | 1 |  | 10 | 5 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
1.3. | 1.3.Certification of sparyers ( application technique) - 1.3 can be solved together with 1.2
1.3.1. | Evaluation of the whole segment (sprayers used on farms, sprayers official distributors, service centers, present practise) | 5 workning-day mission in GE | NFA | CZ expert (s) | 1 |  | 6 | 5 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
1.3.2. | Complex proposal for establishment of system for control/inspection of pesticide spraying equipment (including calibration), Requirements on sprayers calibration (legal basis requirements). Delivery of explanatory lesson. | 4 working day mission to GE, on-line cooperation | NFA (NFA designated technicians) | CZ expert (s) | 1 |  | 8 | 4 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
1.3.3. | Assistance in devolopment of technical requirements for attestation centers | on-line cooperation | NFA, NFA designated technicians | CZ expert (s) | 1 |  | 4 |  |  | Final document delivered in English and Georgian
1.3.4. | Continuation of Initial Workshop - sprayers attestation and calibration | START OF THE PROJECT - JOINED 2 day WORKSHOP FOR 1.1.1, 1.2.1 AND 1.3.4 | NFA, NFA designated technicians, Advisors | CZ expert (s)
2. | ACTIVITY 2 - National database of pesticides statistics
Overall Output - 1 two-day long workshop covering topics a) EU Regulation 2022/2379, b) Traceability and obligatory data records on trade and use of PPP in Czech Republic organized and recommendations in the area of PPP statistics and records provided
2.1. | 0,5 day Workshop on requrements of REGULATION (EC) No 1185/2009 and 2022/2379 | Joined workshop for sub-activity 2.1 and 2.2. Overall combined length of workshop - 1 day. 70 people. | NFA, (statistics organisations) | CZ expert (s)
2.2. | 0,5 day Workshop - Traceability and obligatory data records and on trade and use of PPP in the CZ | Joined workshop for sub-activity 2.1 and 2.2. Overall combined length of workshop - 1 day. 70 people. | NFA, icl. municipality staff, statistic organisation | CZ expert (s) | 1 |  | 3 | 2 | 45 | Simultaneous Translation _ English-Georgian
2.3. | Formulation of reccomendations in area of PPP´statistics (use/trade) and recoords and traceability) | to be solved with preparation of the workshop and in accordance to relevant parts of activities 1 and 4 (requirements on professional users of pesticides and official control requirements) | NFA, icl. municipality staff, statistic organisation | CZ expert (s) | [5 empty] | Final document delivered in English and Georgian
3. | ACTIVITY 3 - Improvement the control of PPPs - laboratory area and control of feed contaminants
Overall Output - As the result of technical assistance, report on Georgian laboratory capacities in the area of testing PPPs elaborated and inputs to new/modification of existing methodology for PPP laboratory analysis provided
3.1. | 3.1. area of pesticides
3.1.1. | Evaluation mission - Evaluation of the equipment of GE laboratories related to analysis of PPPs, used protocols, calibration, chemicals, ect. | 3 day mission | SLA, Multitest, (NFA-control sub-division expert) | CZ expert (s) | 2 |  | 10 | 6 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
3.1.2. | 2 study trips in Czechia - Practical trainings in CZ acredited laboratory - equipment of CZ laboratories, used protocols, calibration, chemicals, preparation of samples, storage of samples, issuing of protocols, data recording. | 2 x 4/5 day stays (1st stay 2024 - 4 days, 2nd stay 2025 - 5 days). 2nd study trip has to be organized in absolutelly same date as joint study trip for 3.1.3, 4.3.1, 4.3.2, 4.3.3, because group of attendees from 2nd study trip of sub-activity 3.1.2 will have for 0,5 day (sub-activity 3.1.3) joint programme with group of attendees from joint study trip 3.1.3, 4.3.1, 4.3.2, 4.3.3. | SLA, Multitest | CZ expert (s) | 2 CZ experts needed for this sub-activity | 3/4 (3 Georgian experts will participate in study trip in 2024, and 4 Georgian experts will participate in study trip in 2025) | 20 (Each from 2 Czech experts will need 10 working days for preparation of this sub-activity and conducting study trip) |  |  | Communication in English during study trip in Czechia. Report from study trips in English
3.1.3. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3. Sub-activity 3.1.3 (length 0,5 day) - Sampling - PPP´s - acredited procedure | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3 in total length of 4 days has to be organized in absolutelly same date as 2nd study trip of sub-activity 3.1.2, because for 0,5 day (sub-activity 3.1.3) these two study trip groups will have same programme. | SLA, Multitest, NFA-control sub-division | CZ expert (s) (Other acreditited lab.) | 1 |  | 2
3.1.4. | Formulation of Reccomendations for GE labotarory equipment (PPP´s analysis) | work in Czechia and online cooperation | SLA, Multitest, (NFA-control sub-division expert) | CZ expert (s) | 2 |  | 6 |  |  | Final document delivered in English and Georgian
3.1.5. | Assistance in preparation of new/modification of existing metodology for PPP laboratory analysis. | work in Czechia and online cooperation | SLA, Multitest, (NFA-control sub-division expert) | CZ expert (s) | 2 |  | 10 |  |  | Final document delivered in English and Georgian
3.2. | 3.2. area of contaminants of feed
3.2.1. | Study trip - Monitoring of non-desirable effects of pesticides usage - action planns for PPP residues and other contaminants in feedings, organisation of controls and sampling, sampling techniques, maintanance and preparation of samples, analysis, used methods, protocols, official procedures, practical demonstrations. | 3 working days in CZ, 20 Georgian experts Study trip has to be organized in period 23-25.09.2024 Contractor will not be responsible for costs connected to a) flight tickets of participants to Czechia and back, b) translation, c) acommodation of participants, d) breakfast and dinners, e) transportation in Czechia. Costs connected a), b), c), d) and e) will be paid by outside of this grant. Contractor will within this study trip pay only sallay of its own experts, lunch, coffee breaks and will book and pay confence hall (or Contractor can use his own conference premise). | NFA, RS, SLA and other state/private Labs | CZ expert (s) | 3 CZ experts needed for this activity | 20 (Georgian experts from NFA, RS, SLA ang other food/agri laboratories will participate in study trip) | 18 (Each from 3 experts will need 6 working days for preparation of this activity and conducting study trip) |  |  | Communication in English or Georgian during study trip to Czechia. Report from study trip in English.
4. | ACTIVITY 4 - Post-authorization control of PPPs
Overall Output - Based on technical assistance, and conducted evaluation, Proposal for improved NFA control practice (methodology) in the area of Post-authorization control of PPPs submitted to NFA and other relevant authorities
4.1. | 2 day workshop - Initial workshop on Pesticides - Legislation, Post-authorization control | 2 day workshop | NFA (incl. municipality staff), SLA, MEPA | CZ expert (s) | 2 |  | 10 | 4 | 45 | Simultaneous Translation _ English-Georgian
4.2. | Evaluation of actual activities of sub-division of NFA for official PPP post control. Evaluation of the inspection practice. Model inspection performed by NFA in front of Czech experts | 2 CZ experts accompaanied by NFA (4 working days) | NFA (SLA, Multitest) | CZ expert (s) | 2 |  | 8 | 8 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
4.3.1. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3. Sub-activity 4.3.1 (length 1,5 days) - Practical training in CZ – a) model inspection, post-authorisation control of packaging, labelling, storage, usage and product quality, incl. protocols, taking of PPP samples for laboratory analysis | 1,5 working days within 4 days long joint study trip. Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3 in total length of 4 days has to be organized in absolutelly same date as 2nd study trip of sub-activity 3.1.2, because for 0,5 day (sub-activity 3.1.3) these two study trip groups will have same programme. | NFA | CZ expert (s) | 2 | 6 | 8 |  |  | Consecutive Translation _ to and from Georgian
4.3.2. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3. Sub-activity 4.3.2 (length 1 day) - Practical training in CZ - b) model control of distributors (import, distribution, trade), records, traceability control methodology/guidelines, EU legislation requirements. | 1 working day within 4 days long joint study trip. Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3 in total length of 4 days has to be organized in absolutelly same date as 2nd study trip of sub-activity 3.1.2, because for 0,5 day (sub-activity 3.1.3) these two study trip groups will have same programme. | NFA | CZ expert (s) | 1 |  | 3
4.3.3. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3. Sub-activity 4.3.3 (length 1 day) - Practical training in CZ- c) model control of PPP use on farms records, traceability control methodology/guidelines, EU legislation requirements.. | 1 working day within 4 days long joint study trip. Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3 in total length of 4 days has to be organized in absolutelly same date as 2nd study trip of sub-activity 3.1.2, because for 0,5 day (sub-activity 3.1.3) these two study trip groups will have same programme. | NFA | CZ expert (s) | 1 |  | 3
4.4. | Proposal for improved NFA inspection practise (methodology) in the area of Post-authorization control of PPPs, and execution of model training inspection according to propossed model | 2 CZ experts accompaanied by NFA (4 working days) | NFA | CZ experts (s) | 2 |  | 10 | 8 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
4.5. | 1 day workshop - Workshop on presentation of new/modified post-registration control methodology proposal in accordance to EU requirements (conclusions of the whole project), and presentation of conclusions of the whole project | 1 day workshop | NFA, (SLA, Mutitest) | CZ expert (s) | 1 |  | 3 | 2 | 45 | Simultaneous Translation _ English-Georgian
5. | ACTIVITY 5 - System of PPP registration and traceability in accordance with Regulation (EC) No 1107/2009
Overall Output: Based on the study and provided technical assistance, a Proposal for PPP approval/registration system was submitted to NFA (including inputs/recommendations for software functions)
5.1. | Detail study of GE national legislation and present PPP registration practise and compliance with EU acquis | 5 days mission | NFA - PPP dept. | CZ experts (s) | 1 |  | 7 | 5 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
5.2. | 2 day long workshop - Workshop EU requirements on PPP approval and registration systém (incl. analysis of different options), explanation of data protection principles | 2 day workshop (20) | NFA, MEPA, cooperating agencies | CZ expert (s) | 1 |  | 6 | 2 | 20 | Consecutive Translation _ to and from Georgian
5.3. | Study trip to CZ - Introduction of the CZ registration systém, incl. PPP register (software) | 4 days , 4 experts | NFA (eventually other cooperating organizations) | CZ expert (s) | 1 | 4 | 6 |  |  | Consecutive Translation _ to and from Georgian. Report from study trip delivered in English.
5.4. | 2 days long workshop on evaluation of physical and chemical properties and chemical equivalence of sources of active substances (I.) | 2 day workshop (20) | NFA,(other cooperating agencies within approval procedure) |  | 1 |  | 6 | 2 | 20 | Consecutive Translation _ to and from Georgian
5.5. | Cz key Expert - Ge key expert (s) - Training and guidance on EC procedures. For more information see Logframe. | 3 day mission |  | CZ expert (s) | 1 |  | 3 | 3 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
5.6. | Continuation Cz key Expert - Ge key expert (s) - Training and guidance. The objectives for further stages of the expert to expert trainings will include: For more information see Logframe. | 3 day mission |  | CZ expert (s) | 1 |  | 3 | 3 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
5.7. | Reccomendations -suitable system of PPP aproval procedure (s) in Georgia (incl. re-registration ) | 5 days mission, correspondent communication | NFA (cooperating agencies) | CZ expert (s) | 1 |  | 12 | 5 |  | Communication in English or Georgian during mission. Final document delivered in English and Georgian
5.8. | Evaluation of software needs for PPP aproval procedure (s) in Georgia and reccommendation of esential software functions (including requirements on these functions) | to be part of sub-activity Reccomendations -suitable system of PPP aproval procedure (s) in Georgia (incl. re-registration ) | NFA (cooperating agencies) | CZ expert (s) | [5 empty] | Final document delivered in English and Georgian
6 | ACTIVITY 6 - Other supporting activities focusing on improvement of Georgian SPS Official Risk-Based Inspection Controls in Phyto area
Overall Output - Training-workshop of monitoring and surveillance control program of selected harmful organisms organized and respective recommendations provided
6.1. | 2 day training-workshop - Training-workshop of monitoring and surveillance control program of selected harmful organisms. [Phyto area of SPS Official risk-based Inspection Controls]. Provision of recommendation connected to monitoring and surveillance of harmful organisms and Official risk-based Inspection Controls. | 2 day workshop (60) | NFA, RS, SRCA SLA, MEPA, Academia | CZ expert (s) | 2 |  | 6 | 4 | 60 | Simultaneous Translation _ English-Georgian
7 | ACTIVITY 7 - Steering Comittee meetings
Overall Output - 3 Steering Committee meetings organized
7.1. | Steering committee meetings | 3 x 0,5 day meetings during assignment | COMPOSITION OF PROJECT STEERING COMMITTEE - EUD, SIDA, FAO, CzDA, Embassy of the Czech Republic, MEPA, implementer, NFA, RS, SLA, Multitest, GeLab |  | 6 |  | 6 | 6 | 20 | Consecutive Translation _ to and from Georgian
Project implementation requires organisation of - 3 x steering comitteees
Service Provider/Recipient of this grant is allowed to use subcontractors.
Administrative and managemental expenditures has to be included into this grant project.
Contribution from Georgian side: 1) In kind contribution of Georgian experts in the form of working hous that will not be reimbursed by the grant project budget, 2) Accomodation and transportation of Georgian participants which will participate in workshops organized in the Tbilisi will be paid either by NFA o by Georgian participants - accomodation and transportation will not be paid from grant project budget. 3) In case of working need - NFA will provide in Georgia outside of Tbilisi personal guidance and will ensure transportation of Czech expert. Costs connected to transport in Georgia outside of Tbilisi will be covered by NFA from NFA's budget).
Note to Language requirements: Expenditures connected to translation has to be part of grant project budget. Requirements for translation are indicated in the column "Language". All documents have to be provided in English and Georgian. The exceptions are reports from study trips to Czechia - reports from study trips to Czechia should be elaborated only in English. PowerPoint presentations have to be in English or Georgian. Small supportive documents such as attendance sheets will be in English.
Within the missions to Georgia, Service Provider/Recipient of Grant is responsible for hotel accomodation of its staff/experts, transportation in Tbilisi, conference rooms rent (including equipment for translation), catering during workshops and coverage of translation services.
Red colour is symbol for study trips of Georgian experts in Czechia. During study trips to Czechia, personal expenditures of Georgian experts can't be covered. Costs during study trip of Georgian experts in Czechia include - international flights tickets, transport during missions in the Czech Republic, accomodation in hotels and whole day food.
Sub-activities highlighted in the same colour are integrated into the same mission (to maximize cost-effectiveness).
Czech Embassy's conference room or CzDA's conference room with capacity of 30 people can be used for appopriate workshops or Steering Committee meetings in Georgia free of charge.