## Annex 7–Harmonogram
2025
|  | IX. | X. | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X.
1. | ACTIVITY 1 - Area of EU directive 128/2009
Overall Output - Initial workshop on requirements of directive 128/2009 organized, Complex proposals for a) certification system of professional users of pesticides, b) establishment of system for control/inspection of pesticide spraying equipment elaborated and submitted to relevant authorities
1.1. | 1.1. Sustainable use of pesticides
1.1.1. | Initial workshops on requirements of directive 128/2009 (initial 2 days workshop joined event for 1.1.1, 1.2.1 and 1.3.4) | x (ideally first half of month)
1.2. | 1.2. Certification of professional users of pesticides
1.2.1. | Continuation of Initial Workshop - certification of profesional PPP users (initial 2 days workshop joined event for 1.1.1, 1.2.1 and 1.3.4) | x (ideally first half of month)
1.2.2. | Evaluation mission - Evaluation of the whole segment of professional users of pesticides in GE (distributors, advisors, services, farmers, other users) | x | x | x
1.2.3. | Reccomendation of definition (s) of professional user of pesticides in Georgia (specification of each category) |  | x | x | x | x
1.2.4. | Assistance in development of training and qualifying/ certification system for different categories of professional users of pesticides (distributors, advisers/consultants/services, farmers) |  |  | x | x | x | x | x | x
1.3. | 1.3.Certification of sparyers ( application technique) - 1.3 can be solved together with 1.2
1.3.1. | Evaluation of the whole segment (sprayers used on farms, sprayers official distributors, service centers, present practise) | x | x | x | x | x
1.3.2. | Complex proposal for establishment of system for control/inspection of pesticide spraying equipment (including calibration), Requirements on sprayers calibration (legal basis requirements). Delivery of explanatory lesson. |  |  | x | x | x | x | x | x
1.3.3. | Assistance in devolopment of technical requirements for attestation centers |  |  |  |  | x | x | x | x | x | x
1.3.4. | Continuation of Initial Workshop - sprayers attestation and calibration (initial 2 days workshop joined event for 1.1.1, 1.2.1 and 1.3.4) | x (ideally first half of month)
2. | ACTIVITY 2 - National database of pesticides statistics
Overall Output - 1 two-day long workshop covering topics a) EU Regulation 2022/2379, b) Traceability and obligatory data records on trade and use of PPP in Czech Republic organized and recommendations in the area of PPP statistics and records provided
2.1. | 0,5 day Workshop on requrements of REGULATION (EC) No 1185/2009 and 2022/2379 | [6 empty] | x | x | x
2.2. | 0,5 day Workshop - Traceability and obligatory data records and on trade and use of PPP in the CZ | [6 empty] | x | x | x
2.3. | Formulation of reccomendations in area of PPP´statistics (use/trade) and recoords and traceability) | [6 empty] | x | x | x | x | x | x
3. | ACTIVITY 3 - Improvement the control of PPPs - laboratory area and control of feed contaminants
Overall Output - As the result of technical assistance, report on Georgian laboratory capacities in the area of testing PPPs elaborated and inputs to new/modification of existing methodology for PPP laboratory analysis provided
3.1. | 3.1. area of pesticides
3.1.1. | Evaluation mission - Evaluation of the equipment of GE laboratories related to analysis of PPPs - used protocols, calibration, chemicals, ect. | x | x | x
3.1.2. | 2 study trips in Czechia - Practical trainings in CZ acredited laboratory - equipment of CZ laboratories, used protocols, calibration, chemicals, preparation of samples, storage of samples, issuing of protocols, data recording. | 1st study trip has to be organized in 2024 and 2nd study trip has to be organized in 2025. 2nd study trip has to be organized in absolutelly same date as joint study trip for 3.1.3, 4.3.1, 4.3.2, 4.3.3, because group of attendees from 2nd study trip of sub-activity 3.1.2 will have for 0,5 day (sub-activity 3.1.3) joint programme with group of attendees from joint study trip 3.1.3, 4.3.1, 4.3.2, 4.3.3. | x | x |  |  |  |  | X | X
3.1.3. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3. Sub-activity 3.1.3 (length 0,5 day) - Sampling - PPP´s - acredited procedure | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3 in total length of 4 days has to be organized in absolutelly same date as 2nd study trip of sub-activity 3.1.2, because for 0,5 day (sub-activity 3.1.3) these two study trip groups will have same programme. | [6 empty] | x | x
3.1.4. | Formulation of reccomendations for GE labotarory equipment (PPP´s analysis) |  |  |  | x | x | x | x | x | x | x
3.1.5. | Assistance in preparation of new/modification of existing metodology for PPP laboratory analysis. |  |  | x | x | x | x | x | x | x | x
3.2. | 3.2. area of contaminants of feed
3.2.1. | Study trip - Monitoring of non-desirable effects of pesticides usage - action planns for PPP residues and other contaminants in feed, organisation of controls and sampling, sampling techniques, maintanance and preparation of samples, analysis, used methods, protocols, official procedures, practical demonstrations. | Study trip has to be organized in period 23-25.09.2024 Contractor will not be responsible for costs connected to a) flight tickets of participants to Czechia and back, b) translation, c) acommodation of participants, d) breakfast and dinners, e) transportation in Czechia. Costs connected a), b), c), d) and e) will be paid by outside of this grant. Contractor will within this study trip pay only sallay of its own experts, lunch, coffee breaks and will book and pay confence hall (or Contractor can use his own conference premise).
4. | ACTIVITY 4 - Post-authorization control of PPPs
Overall Output - Based on technical assistance, and conducted evaluation, Proposal for improved NFA control practice (methodology) in the area of Post-authorization control of PPPs submitted to NFA and other relevant authorities
4.1. | 2 day workshop - Initial workshop on Pesticides - Legislation, Post-authorization control |  | x | x
4.2. | Evaluation of actual activities of sub-division of NFA for official PPP post control. Evaluation of the inspection practice. Model inspection performed by NFA in front of Czech experts | [5 empty] | x | x | x | x | x | x | x
4.3.1. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3. Sub-activity 4.3.1 (length 1,5 days) - Practical training in CZ – a) model inspection, post-authorisation control of packaging, labelling, storage, usage and product quality, incl. protocols, taking of PPP samples for laboratory analysis | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3 in total length of 4 days has to be organized in absolutelly same date as 2nd study trip of sub-activity 3.1.2, because for 0,5 day (sub-activity 3.1.3) these two study trip groups will have same programme. | [6 empty] | x | x
4.3.2. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3. Sub-activity 4.3.2 (length 1 day) - Practical training in CZ - b) model control of distributors (import, distribution, trade), records, traceability control methodology/guidelines, EU legislation requirements. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3 in total length of 4 days has to be organized in absolutelly same date as 2nd study trip of sub-activity 3.1.2, because for 0,5 day (sub-activity 3.1.3) these two study trip groups will have same programme. | [6 empty] | x | x
4.3.3. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3. Sub-activity 4.3.3 (length 1 day) - Practical training in CZ- c) model control of PPP use on farms records, traceability control methodology/guidelines, EU legislation requirements. | Joint study trip for 4.3.1, 3.1.3, 4.3.2, and 4.3.3 in total length of 4 days has to be organized in absolutelly same date as 2nd study trip of sub-activity 3.1.2, because for 0,5 day (sub-activity 3.1.3) these two study trip groups will have same programme. | [6 empty] | x | x
4.4. | Proposal for improved NFA inspection practise (methodology) in the area of Post-authorization control of PPPs, and execution of model training inspection according to propossed model | [8 empty] | x | x | x | x | x | x
4.5. | 1 day workshop - Workshop on presentation of new/modified post-registration control methodology proposal in accordance to EU requirements, and presentation of conclusions of the whole project | [11 empty] | x | x | x
5. | ACTIVITY 5 - System of PPP registration and traceability in accordance with Regulation (EC) No 1107/2009
Overall Output: Based on the study and provided technical assistance, a Proposal for PPP approval/registration system was submitted to NFA (including inputs/recommendations for software functions)
5.1. | Detail study of GE national legislation and present PPP registration practise and compliance with EU acquis |  | x | x | x | x | x
5.2. | 2 day long workshop - Workshop EU requirements on PPP approval and registration system (incl. analysis of different options), explanation of data protection principles |  |  | x | x | x
5.3. | Study trip to CZ - Introduction of the CZ registration system, incl. PPP register (software) |  |  |  | x | x | x | x
5.4. | 2 day long workshop on evaluation of physical and chemical properties and chemical equivalence of sources of active substances |  |  | x | x | x | x
5.5. | Cz key Expert - Ge key expert (s) - Training and guidance on EC procedures. For more information see Logframe. |  | x | x | x | x | x | x | x | x | x | x | x | x | x
5.6. | Continuation Cz key Expert - Ge key expert (s) - Training and guidance. The objectives for further stages of the expert to expert trainings will include: For more information see Logframe. |  | x | x | x | x | x | x | x | x | x | x | x | x | x
5.7. | Reccomendations -suitable system of PPP aproval procedure (s) in Georgia (incl. re-registration ) |  | x | x | x | x | x | x | x | x | x | x | x | x | x
5.8. | Evaluation of software needs for PPP aproval procedure (s) in Georgia and reccommendation of esential software functions (including requirements on these functions) |  | x | x | x | x | x | x | x | x | x | x | x | x | x
6 | ACTIVITY 6 - Other supporting activities focusing on improvement of Georgian SPS Official Risk-Based Inspection Controls in Phyto area
Overall Output - Training-workshop of monitoring and surveillance control program of selected harmful organisms organized and respective recommendations provided
6.1. | 2 day training-workshop - Training-wokshop of monitoring and surveillance control program of selected harmful organisms. [Phyto area of SPS Official risk-based Inspection Controls]. Provision of recommendation connected to monitoring and surveillance of harmful organisms and Official risk-based Inspection Controls. |  |  | x | x
7 | ACTIVITY 7 - Steering Comittee meetings
Overall Output - 3 Steering Committee meetings organized
7.1 | Steering committee meetings |  |  | x | x |  |  |  | x | x |  |  |  | x | x
typing in red - technical visits of GE experts to CZ
typing in purple - workshops/trainings by CZ experts in Tbilisi GE